## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group 9-2021 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Wade | Walker | Luke
Project Start Date: | 2021-11-13 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 1 | time axis 2021-11-14 to 2022-01-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-14 to 2022-01-08
Iteration 01
Iteration planning and meeting | Goal | Walker | 25% | 2021-11-13 | 1
Complete stakegholder register | Milestone | Wade | 80 | 2021-11-16 | 2 | bar: 2021-11-16 to 2021-11-17
Design persona | Low Risk | Luke | 100% | 2021-11-18 | 3
Review and test persona | Milestone | Chi Minming | 10% | 2021-11-28 | 4 | bar: 2021-11-28 to 2021-12-01
Complete progress report | Milestone | Walker | 10% | 2021-12-03 | 2 | bar: 2021-12-03 to 2021-12-04
Iteration 02
Start creating git branch | High Risk |  | 100% | 2021-11-19 | 1
Websits Planning | Med Risk |  | 100% | 2021-11-21 | 3
scheduling | Milestone |  | 100% | 2021-11-26 | 4 | bar: 2021-11-26 to 2021-11-29
Continue project development | High Risk |  | 100% | 2021-11-28 | 11
Complete progress report | Milestone |  | 100% | 2021-11-29 | 2 | bar: 2021-11-29 to 2021-11-30
Iteration 03
Create and write HTML;txt; files | Low Risk |  | 100% | 2021-11-28 | 4
Connection between pull file and GitHub remote database | High Risk |  | 100% | 2021-12-01 | 10
Check the pulling process | On Track |  | 100% | 2021-12-16 | 1
Test the operation of the website and find problems, | Milestone |  | 100% | 2021-12-20 | 10 | bar: 2021-12-20 to 2021-12-29
Complete progress report | Low Risk |  | 100% | 2021-12-03 | 2
Final
Successfully developed and run the website | Goal |  | 100% | 2021-12-23 | 1 | 2021-12-23: 2
To add more data, Insert new rows ABOVE this one
Formulas:
Wade = IFERROR(IF(MIN(Milestones4352[Start])=0,TODAY(),B11(Milestones4352[Start])),TODAY())

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-13 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 1 | time axis 2021-11-14 to 2022-01-08
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-13 | 3 | S: 2; M: 2
Task 2 | Milestone |  |  | 2021-11-18 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2021-11-10 | 10
Task 4 | Milestone |  |  | 2021-12-03 | 1 | bar: F
Task 5 | Med Risk |  | 10% | 2021-11-19 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-19 | 13
Task 2 | On Track |  | 50% | 2021-11-21 | 9
Task 3 | Low Risk |  | 33% | 2021-11-26 | 11
Task 4 | Milestone |  |  | 2021-11-28 | 1 | bar: S
Task 5 |  |  |  | 2021-11-29 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-28 | 4
Task 2 | Med Risk |  |  | 2021-12-01 | 14
Task 3 | On Track |  |  | 2021-12-16 | 6
Task 4 | Goal |  |  | 2021-12-20 | 3 | M: 2; T: 2; W: 2
Task 5 | Low Risk |  |  | 2021-11-19 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-23 | 15
Task 2 |  |  |  | 2022-01-06 | 5
Task 3 | Milestone |  |  | 2022-02-17 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-13 |  |  |  |  | November | [13 empty] | December | [34 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-18 to 2022-01-12
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-18 to 2022-01-12
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-13 | 3
Task 2 | Milestone |  |  | 2021-11-18 | 1 | bar: 2021-11-18
Task 3 | Low Risk |  | 50% | 2021-11-10 | 10
Task 4 | Milestone |  |  | 2021-12-03 | 1 | bar: 2021-12-03
Task 5 | Med Risk |  | 10% | 2021-11-19 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-19 | 13
Task 2 | On Track |  | 50% | 2021-11-21 | 9
Task 3 | Low Risk |  | 33% | 2021-11-26 | 11
Task 4 | Milestone |  |  | 2021-11-28 | 1 | bar: 2021-11-28
Task 5 |  |  |  | 2021-11-29 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-28 | 4
Task 2 | Med Risk |  |  | 2021-12-01 | 14
Task 3 | On Track |  |  | 2021-12-16 | 6
Task 4 | Goal |  |  | 2021-12-20 | 3 | 2021-12-20: 2; 2021-12-21: 2; 2021-12-22: 2
Task 5 | Low Risk |  |  | 2021-11-19 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-23 | 15
Task 2 |  |  |  | 2022-01-06 | 5
Task 3 | Milestone |  |  | 2022-02-17 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one